## Sheet1
Module Name | Feature | Test Case ID | Test Case Description | Pre-Condition | Steps to Execute | Test Data | Expected Result | Actual Result | Status | Revised by | Comment
Registration Modal | Registration Modal | TC01 | Verify that the registration modal pops up | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button | 1- User has fulfilled pre-conditions 2- User has clicked on Register on the Log in Modal. | N/A | Register modal should pop up on the screen | Register modal has popped up on the screen | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Registering Successfully | TC02 | Verify that the user can register succesfully after filling all the fields | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal. | 1- User has fulfilled pre-conditions 2- User has filled in all the fields in the Registration Modal 3- User has entered a pasword with mat least 6 characters 4- User has clicked the Sign Up button | Username, email address, password, password confirmation | User should be able to register successfully and be taken back to the landing page of the website. Upon clicking on the log in button again, a message should say that the registration was successful | User has registered successfully and was taken to the landing page of the website | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Registration due to Existing Username | TC03 | Verify that the user cannot use an existing username to register | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal. | 1- User has fulfilled pre-conditions 2- User has filled in all the fields in the Registration Modal 3- User has used an existing username to register 4- User has entered a pasword with at least 6 characters 5- User has clicked the Sign Up button | Username | User registration should not be allowed and a message should pop up on the registration modal notifying the user that the username already exists. | User registration is not allowed and a message is shown on the registration modal notifying the user that the username already exists. | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Registration due to Existing Email | TC04 | Verify that the user cannot use an existing email address to register | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal. | 1- User has fulfilled pre-conditions 2- User has filled in all the fields in the Registration Modal 3- User has used an existing email address to register 4- User has entered a pasword with at least 6 characters 5- User has clicked the Sign Up button | Email Address | User registration should not be allowed and a message should pop up on the registration modal notifying the user that the email address has already been registered with. | User registration is not allowed and a message is shown on the registration modal notifying the user that the email address has already been registered with. | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Registration due to invalid email | TC05 | Verify that the user cannot use an invalid email address to register | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal. | 1- User has fulfilled pre-conditions 2- User has filled in all the fields in the Registration Modal 3- User has used an invalid email address to register 4- User has entered a pasword with at least 6 characters 5- User has clicked the Sign Up button | Email Address | User registration should not be allowed and a pop up should appear on the registration modal notifying the user that the email address is incomplete | User registration is not allowed and a pop up appears on the registration modal notifying the user that the email address is incomplete | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Registration due to Password | TC06 | Verify that the user cannot register with a password of less than 6 characters | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal. | 1- User has fulfilled pre-conditions 2- User has filled in all the fields in the Registration Modal 4- User has entered a pasword with less than 6 characters 5- User has clicked the Sign Up button | Password | User registration should not be allowed and a message should pop up on the registration modal notifying the user that the password has to be at least 6 characters long | User registration is not allowed and a message is shown on the registration modal notifying the user that the password must be at least 6 characters long | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Registration due to Mismatching Password | TC07 | Verify that the password must match with the password confirmation while registering | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal. | 1- User has fulfilled pre-conditions 2- User has filled in all the fields in the Registration Modal 4- User has entered a password confirmation that differs from the password they entered initially 5- User has clicked the Sign Up button | Password | User registration should not be allowed and a message should pop up on the registration modal notifying the user that the passwords do not match | User registration is not allowed and a message is shown on the registration modal notifying the user that the passwords do not match | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
Log in Modal | Log in Modal | TC08 | Verify that the Log in modal pops up | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button | N/A | Log in modal should pop up on the screen | Log in modal has popped up on the screen | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Logging in Successfully | TC09 | Verify that the user can Log in successfully after filling all the fields | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal 4- User has already registered | 1- User has fulfilled pre-conditions 2- User has clicked on the Log in button 3- User enters a valid email address and password 4- User clicks Login button | Email Address, Password | User should be able to log in successfully and be taken to the landing page of the wesbite | User has logged in successfully and has been taken to the landing page of the wesbite | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Log in due to incorrect Email Address | TC10 | Verify that the user can not Log in using an invalid/unregistered email address | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal 4- User has already registered | 1- User has fulfilled pre-conditions 2- User has clicked on the Log in button | Email Address | User should not be able to log in and a message should pop up on the Log in Modal notifying the user that the email entered is not registered | User is not able to log in and a message has popped up on the Log in Modal notifying the user that the email entered is not registered | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Log in due to incorrect Password | TC11 | Verify that the user can not Log in using an invalid password | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button 3-User has clicked on Register on the Log in Modal 4- User has already registered | 1- User has fulfilled pre-conditions 2- User has clicked on the Log in button | Password | User should not be able to log in and a message should pop up on the Log in Modal notifying the user that the password is incorrect | User is not able to log in and a message has popped up on the Log in Modal notifying the user that the password is incorrect | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
Forgot Password Modal | Forgot Password Modal | TC12 | Verify that the Forgot Password Modal shows up | 1- User has launched https://gimmickgames-1.onrender.com 2- User has clicked on the Log in button | 1- User has fulfilled pre-conditions 2- User has clicked on Recover Password | N/A | Forgot Password Modal should pop up on the screen, pressing the Back button should send the user back to the Log in Modal | Forgot Password Modal has popped up on the screen, pressing the Back button sends the user back to the Log in Modal | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Password Recovery | TC13 | Verify that the user can recover their password successfully | 1- User has launched https://gimmickgames-1.onrender.com 2- User has already registered 3- User has clicked on the Log in button 4- User has clicked on Recover Password | 1- User has fulfilled pre-conditions 2- User has entered a valid email address 3- User has clicked on Send OTP 4- User checks their email inbox and spam folders for password recovery email from gimmickgames 5- User types in OTP 6- User clicks Submit OTP 7-User enters new password and password confirmation 8- User clicks Continue 9- User is redirected to Log in Modal | Email Address | A message should inform the user that the OTP was sent. User should receive an email with an OTP in their inbox/spam folder. After inputting the correct OTP, a message should inform the user that the OTP is confirmed and prompt the user to change their password in another Modal. After changing their password the user is redirected to the Log in modal with a message informing the user that the password has changed successfully | The message of the sent OTP is displayed. User has received an email with an OTP in their inbox/spam folder. Using the correct OTP the user was able to reset their password successfully. The user was redirected to the Log in modal and the message displayed the correct information | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Password Recovery due to invalid email | TC14 | Verify that the user cannot use an invalid email address to recover their password | 1- User has launched https://gimmickgames-1.onrender.com 2- User has already registered 3- User has clicked on the Log in button 4- User has clicked on Recover Password | 1- User has fulfilled pre-conditions 2- User has entered an invalid email address | Email Address | User should receive a message in the Forgot Password Modal that the email has not been found | User has received a message in the Forgot Password Modal that the email has not been found | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Password Recovery due to invalid OTP | TC15 | Verify that the user cannot use an invalid OTP to recover their password | 1- User has launched https://gimmickgames-1.onrender.com 2- User has already registered 3- User has clicked on the Log in button 4- User has clicked on Recover Password | 1- User has fulfilled pre-conditions 2- User has entered an invalid OTP | OTP | A message should inform the user that the OTP is incorrect and prompt the user to re-enter the correct OTP | The message informs the user that the OTP is confirmed and prompts the user to change the password even though the modal still requires inputting the correct OTP | FAIL | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed Password Recovery due to Mismatching Passwords | TC16 | Verify that the user cannot use an mismatching passwords for password recovery | 1- User has launched https://gimmickgames-1.onrender.com 2- User has already registered 3- User has clicked on the Log in button 4- User has clicked on Recover Password 5- User has entered a valid OTP | 1- User has fulfilled pre-conditions 2- User has entered two different passwords in the password and password confirmation fields | Password | The user should not be able to change the password and a message should inform the user that the passwords do not match. | The user was not be able to change the password and a message informed the user that the passwords do not match. | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
Landing Page | Landing Page Appears Before Logging In | TC17 | Verfiy that the landing page appears when the user enters the correct URL, without logging in | 1-User has not logged in 2- User has launched https://gimmickgames-1.onrender.com | 1-User has not logged in 2- User has launched https://gimmickgames-1.onrender.com | N/A | The user should see the landing page before even logging in once the URL is typed in | Without logging in, the landing page appears once the URL is passed | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Landing Page Appears After Logging In | TC18 | Verfiy that the landing page appears when the user enters the correct URL after logging in | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in | 1- User has fulfilled pre-conditions 2- User has clicked on the Log in button 3- User enters a valid email address and password 4- User clicks Login button | Email Address, Password | User should be able to log in successfully and be taken to the Landing Page of the wesbite | User has logged in successfully and has been taken to the Landing Page of the wesbite | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Redirecting To Games Leaderboards Through Game Images | TC19 | Verify that the user will be taken to the respective game leaderboards after clicking on either game images in the landing page | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in/has not logged in | 1- User has fulfilled pre-conditions 2- User has clicked on either game images in the Landing Page | N/A | User should be redirected to the repective Game Leaderboards after clicking on either images in the Landing Page | User is redirected to the repective Game Leaderboards after clicking on either images in the Landing Page | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Redirecting to Game Leaderboards using Navigation Bar Links | TC20 | Verify that the links in the Navigation Bar take the user to the correct game leaderboard pages | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in/has not logged in | 1- User has fulfilled pre-conditions 2- User has clicked on either the Snake Game link or the Space Invaders link in the Navigation Bar | N/A | User should be redirected to the Snake Game Leaderboard or the Space Invaders Game Leaderboard | User is redirected to the Snake Game Leaderboard or the Space Invaders Game Leaderboard | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Redirecting to Landing Page | TC21 | Redirecting to Landing Page By Clicking On The Logo Or The Website Name in the Navigation Bar | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in/has not logged in | 1- User has fulfilled pre-conditions 2- User has clicked on either the Logo or the Gimmick Games link in the Navigation Bar | N/A | Whether they are logged in or not, user should be redirected to the Landing Page upon clicking either the logo or the Gimmick Games link in the Navigation Bar | Whether they are logged in or not, user is redirected to the Landing Page upon clicking either the logo or the Gimmick Games link in the Navigation Bar | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Redirecting to Profile Page | TC22 | Verify that the My Profile link in the Navigation Bar takes the user to their Profile Page | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in | 1- User has fulfilled pre-conditions 2- User has clicked on either the My Profile link in the Navigation Bar | N/A | User should be able to view to their profile upon clicking the My Profile link | User is directed and is able to view to their profile | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Logging out | TC23 | Verify that the user can log out using the Log out button in the Navigation Bar | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in | 1- User has fulfilled pre-conditions 2- User has clicked on the Log out button in the Navigation Bar | N/A | User should be able to log out and be redirected from any page to the Landing Page | User is logged out and is redirected from any page to the Landing Page | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
Profile Page | Viewing User Profile | TC24 | Verify that the user can view their profile page | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in | 1- User has fulfilled pre-conditions 2- User has clicked on the My Profile link in the Navigation Bar | N/A | User should be able to view their profile upon clicking the My Profile link in the Navigation Bar | User is able to view their profile upon clicking the My Profile link in the Navigation Bar | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Updating the email address successfully | TC25 | Verify that the user can change their email address | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in 3- User has clicked on the My Profile link in the Navigation Bar | 1- User has fulfilled pre-conditions 2- User has changed their email address 3- User has clicked on Update Profile button | Email Address | User should be able to update their email address successfully upon clicking the Update Profile button. A message should be displayed informing the user that their profile was updated successfully | User is able to update their email address successfully upon clicking the Update Profile button. A message is displayed informing the user that their profile was updated successfully | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Updating the username successfully | TC26 | Verify that the user can change their username | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in 3- User has clicked on the My Profile link in the Navigation Bar | 1- User has fulfilled pre-conditions 2- User has changed their username into a unique username 3- User has clicked on Update Profile button | Username | User should be able to update their username successfully upon clicking the Update Profile button. A message should be displayed informing the user that their profile was updated successfully | User is able to update their username successfully upon clicking the Update Profile button. A message is displayed informing the user that their profile was updated successfully | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed to update username | TC27 | Verify that the user cannot update their username to an existing username | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in 3- User has clicked on the My Profile link in the Navigation Bar | 1- User has fulfilled pre-conditions 2- User has changed their username into an existing username 3- User has clicked on Update Profile button | Username | User should not be able to update their profile. A message should be notify the user that the username already exists. | User is not able to update their profile. A message notifies the user that the username already exists. | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Failed to Update Email Address | TC28 | Verify that the user cannot update their email address to an invalid email address | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in 3- User has clicked on the My Profile link in the Navigation Bar | 1- User has fulfilled pre-conditions 2- User has changed their email address to an invalid email address 3- User has clicked on Update Profile button | Email Address | User should not be able to update their profile. A message should be notify the user that the email address is invalid | User should not be able to update their profile. A message should be notify the user that the email address is invalid | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Change Password Successfully | TC29 | Verify that the user is able to update their password in their profile | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in 3- User has clicked on the My Profile link in the Navigation Bar | 1- User has fulfilled pre-conditions 2- User has changed their password and confirmed it. 3- User has clicked Click uncover password to see their password 3- User has clicked on Update Profile button | Password | User should be able to see their password upon clicking Click uncover password and be able to change it upon clicking the Update Profile. A message should notify the user that their profile has been updated successfully | User is able to see their password upon clicking Click uncover password and can to change it upon clicking the Update Profile. A message notifies the user that their profile has been updated successfully | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Deleting user Profile | TC30 | Verify that the user can delete their profile | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in 3- User has clicked on the My Profile link in the Navigation Bar | 1- User has fulfilled pre-conditions 2- User has clicked Delete your profile button | N/A | Updated the username succ+essfully | User is able to delete their profile succesfully upon clicking the Delete your profile button and is redirected to the Landing Page | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
Snake Game / Space Invaders Leaderboard Page | Viewing Snake Game / Space Invaders Leaderboard | TC31 | Verify that the user can view the Snake Game / Space Invaders Leaderboard | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in/has not logged in | 1- User has fulfilled pre-conditions 2- User has clicked on the Snake Game/Space Invaders link in the Navigation Bar or Snake Game/Space Invaders Image in the Landing Page | N/A | User should be redirected to the Snake Game Leaderboard or the Space Invaders Game Leaderboard | User is redirected to the Snake Game Leaderboard or the Space Invaders Game Leaderboard | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
Snake Game / Space Invaders Game Page | Viewing Snake Game / Space Invaders Game | TC32 | Verify that the user can view the Snake Game / Space Invaders Game | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in/has not logged in 3- User has clicked on the Snake Game/Space Invaders link in the Navigation Bar or Snake Game/Space Invaders Image in the Landing Page | 1- User has fulfilled pre-conditions 2- User has clicked on the Snake Game/Space Invaders card in the Snake Game/Space Invaders Leaderboard Page | N/A | User should be redirected to the Snake Game or the Space Invaders Game and be able to play either games | User is redirected to the Snake Game or the Space Invaders Game and is able to play either games | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A
| Play Again button | TC33 | Verify that user is able to play the game again successfully after clicking the Play again button once they have lost in the game | 1- User has launched https://gimmickgames-1.onrender.com 2- User has logged in/has not logged in 3- User has clicked on the Snake Game/Space Invaders link in the Navigation Bar or Snake Game/Space Invaders Image in the Landing Page 4- User has clicked on the Snake Game/Space Invaders card in the Snake Game/Space Invaders Leaderboard Page | 1- User has fulfilled pre-conditions 2- User has clicked on the Play again button | N/A | User should be able to play either games again. The user's score should be saved in the game's Leaderboard Page. If the user is logged in, their score should appear in their profile | User is able to play either games again. The user's score is saved in the game's Leaderboard Page. If the user is logged in, their score appears in their profile | PASS | Abdulmohaimin Bashir Muhammad Bilal | N/A